## CRNA Public Record
Copper Rive Native Association Tribal Health Consortia
Tribal Response Program (TRP) Inventory List
Site Name | Location | Coordinates | Landowner | Current Use | Contacts/Staff | Size | Contaminates | Institutional Controls | Action Information | Status | Comments
Old BIA Copper Center School | Old Richardson Highway, 1.3 miles N/NW of Copper Center, AK | Lat: 61.972317; Long: -145.319573 | AK DNR | Abandoned BIA school | Copper River Native Association, Native Village of Klui-Kaah, AK DNR | 4,788 sq ft | Water outfall piping, partially buried 55-gal drum, two utility connection points, former AST site, vertical pipe protruding from ground, large rectangular ditch; diesel, gas, BTEX, asbestos, lead based paint | Windows and doors boarded up to prevent access. | June 7, 2010: Phase I and II Site Assessments completed. March 2020: Currently working with Kluti-Kaah and DNR on reuse plan and funding. | Site Assessment Complete. | CRNA is working with DNR and Kluti-Kaah Village to find cleanup funding options.
Knoebell's service station | Southeast of Glennallen; M 183 Richardson Highway | Lat: 62 06' 21.86"N; Long: -145 38'46.41"W | Rami Caohan | Old gas station/auto shop | Native Village of Tazlina, Copper River Native Association | 2.76 ac | Fuel, oil, waste-electrical waste-ground contaminates |  | Feb 17, 2020: Submitted DBAC for site assessment | DBAC submitted.
Bornite Site | 2nd left on Copperville Rd on left side | Lat: 62.0706948; Long: -145.4177427 |  | Abandoned/junk yard | Copper River Native Association | 0.2 ac | Petroleum, oil, lead paint, asbestos |  | March 2020: Attempted to contact landowner | Inactive | CRNA is trying to find landowner to contact them about cleaning up property.

## Public Record
Copper River Native Association Tribal Health Consortium
Tribal Response Program (TRP) Public Record
Site Name | Location | Coordinates | Area | Contaminates | Contacts/Staff | Institutional Controls | Action Information | Status
Mentasta Traditional Council Building | 6 Mile Mentasta Lake Road, Mentasta Lake, AK 99780 | Lat: 62.930265; Long: -143.797735 |  | Multiple releases of arctic grade diesel (#1) fuel; aboveground storage tank (AST); heating oil AST | Michael Hooper |  | 7/19/2018: Spoke with RP on phone, they are going to contact EPA's IGAP program regarding funding | Active
Mentasta School | 6 Miles off the Tok Cutoff of the Glenn Highway, 38 miles south of Tok Junction, Mentasta Lake, AK 99780 | Lat: 62.929500; Long: -143.797800 |  | two 9,000 gallon diesel USTs spills and overfills; 19,000 ppm DRO contamination; 4,50 ppm DRO contamination | IC Unit | Monitoring of DW well required every other year. | 10/7/2016: Follow up IC reminder letter issued. | Cleanup Complete-Institutional Controls
Mentasta Village Clinic | PO Box 600, Mentasta Lake, AK 99780 | Lat: 62.902500; Long: -143.748090 | Approx 350 cy | 300 gal heating fuel tank | IC Unit | Advance approval required to transport soil or groundwater off-site. | 6/11/2012: This site meets the 2009 closure policy requirements therefore IC's can be removed. The default requirement of no offsite transport of soil and groundwater from this site will still apply. | Cleanup Complete
Mentasta Lodge | MP 78.1 Tok Cutoff Highway, Gakona, AK 99586 | Lat: 62.888757; Long: -143.678746 | Approx 175 cy | 1 5,000 gal unleaded gas UST and 1 1,000 gal diesel automotive fuel UST | IC Unit | Advance approval required to transport soil or groundwater off-site. | 7/9/2013: The conditions at this site meet the 2009 closure policy, therefore IC's can be removed. The default requirement of no offsite transport of soil or groundwater will still apply. In accordance with 18 AAC 78.276(f)(2), ADEC may require additional site assessment, monitoring, remediation, and other necessary action at this facility should new information become available that indicates contamination at this site may pose a threat to human health or the environment. | Cleanup Complete
FAA Slana Station | Mile 64.8 Tok Cutoff, Slana, AK 99586 | Lat: 62.724694; Long: -143.866556 |  | 1,000 gal regulated underground storage tank, 55 gal drum incinerator; former aboveground storage tank, fuel line utility chase with sides but no bottom | Bob Glascott | Advance approval required to transport soil or groundwater off-site. | 6/19/2003: Site closure approval | Cleanup Complete
Duffys Roadhouse | Mile 62.7 Tok Cutoff; SR Box 370, Gakona, AK 99586 | Lat: 62.724786; Long: -143.914464 | Approx 30 cy | 2 2,000 gal unleaded gas USTs |  | Advance approval required to transport soil or groundwater off-site. | 2/10/1997: CLOS; Closure letter issued. Comments: Rushe 3/3/97 preliminary closure ltr. By DEC at request of RP not accepted by buyer. Buyer wanted final ltr issued 2/10/97 describing in detail cleanup actions conducted. | Cleanup Complete
ADOTPF – Slana Maintenance Station | 60 Mile Tok Cutoff, then 1/2 mile down Nebesna Rd, Slana, AK 99586 | Lat: 62.708467; Long: -143.978826 | Approx 1,200 cy | One 2,000 gal diesel UST, one 8,000 gal diesel UST, two 2,000 gal gas USTs | IC Unit | Movement or use of contaminated material (including on site) in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70). Advance approval required to transport soil or groundwater off site. | 2/19/2019: The drinking water well was sampled durin the Dec 2018 injection well decommissioning. The water was sampled for volatile organic compounds (VOCs) which did not contains analytes above the Table C cleanup levels. The 2006 groundwater monitoring requirement will be removed for this site. All other institutional controls requirements will remain in place. | Cleanup Complete-Institutional Controls
ADOT&PF Slana Maintenance Station Class V Injection Well | 60 Mile Tok Cutoff, then 1/2 mile down Nebesna Rd, Slana, AK 99586 | Lat: 62.707519; Long: -143.978239 |  | Three injection wells | Michael Hooper |  | 12/7/2018: Site status changed to Active based on Site Characterization results during injection well decommissioning. Primary contaminant remaining following injection well decommissioning is DRO below human health levels, but above MTGW cleanup levels. Groundwater is estimated at 80 ft below grade. | Active
High Frequency Active Auroral Research Program (HAARP) | MP 11.3 Tok Cutoff, Gakona, AK 9986 | Lat: 62.391177; Long: -145.131447 | Approx 3 cy | Spill-two diesel generators | John Halverson | Advance approval required to transport soil or groundwater off-site. | 1/29/2015: DEC received and filed a Memorandum for Record from the AF updating the Environmental Baseline Survey (EBS) by documenting regulatory closure of th "category 2 area" where DRO had been found at a low concentration (580 mg/kg) that was above the method 2 migration to groundwater cleanup level. As noted in the Nov 12, 2014 DEC letter, the migration to groundwater cleanup levels were determined to not apply at the site due to permafrost. | Cleanup Complete
Heinz Salvage Yard Gakona | MP 4.7 Tok Cutoff, Gakona, AK 99586 | Lat: 62.312873; Long: -145.217487 |  | Numerous junk vehicles, fuel, glycols, oil, break fluid, gear lube, transmission fluid, batteries, storage tanks, drums | Lisa Griswold |  | 5/16/2019: Initial ranking with ETM completed for source area id: 80454 name: Burn pit | Informational
Gulkana NALEMP | MP 127.5 Richardson HWY, Gakona, AK 99586 | Lat: 62.273547; Long: -145.387219 | 6ft x 8ft x 4ft | Contained oil and diesel fuel | John O'Brien |  | 8/16/2019: DEC approved the Final North Bluff Dumpsite and Northwest Access Road Areas Site Assessment, Site Investigation, and Debris Removal Report Dated August 2019. | Active
Gulkana Prepositioning Area & Army Site FUDS | N of Jct of Glenn & Richardson Hwys, N & NE, and S of Gulkana Airport, Gakona, AK 9586 | Lat: 62.273547; Long: -145.387219 | 5,044 ac | 3 full drums | John O'Brien |  | 9/18/2006: Staff reviewed START report, 1993 Field Investigation, Gulkana Inventory Report and various memos. The 93 report indicates there were 3 full drums left at the current Ellis Air taxi of military origins. Staff had been requested to concur with a closure for the CON/HTRW project but until the disposition of those three drums is determined, a decision can not be made. | Active
FAA Gulkana Former Diesel AST Tank Farm | Gulkana Airport, Adjacent to and beneath ADOT&PF Equipment Storage Bldg, Glennallen, AK 99588 | Lat: 62.159110; Long: -145.461651 | 6,282 cy | 6 large, vertical diesel ASTs in a diked area; petroleum | Debra Caillouet | Advance approval required to transport soil or groundwater off-site. | 11/21/2012: The 2006 Site investigation maximum DRO detected 4600 mg/kg at 5-7' bgs for tank 3 and 4520 mg/kg DRO for tank 4 at 15-17' bgs. Additional borings outside of the former tank farm did not find DRO above this levels. No recoverable groundwater was found. | Cleanup Complete
FAA Gulkana Bldg 303 | Gulkana Airport Building 303, Glennallen, AK 99588 | Lat: 62.158856; Long: -145.461571 | 4,385 cy | 1,000 gal heating oil UST, gas pump, former gas AST | Gretchen Caudill |  | 5/15/2018: Report or Workplan Review-other | Active
ADOT&PF Gulkana Maintenance Station Class V Injection Well | Mile 118.1 Richardson Hwy, Glennallen, AK 99588 | Lat: 62.158778; Long: -145.460775 | 7.5ft x 38ft | Injection well | Michael Hooper |  | 6/13/2019: Meeting or teleconference held | Active
FAA Gulkana Engine Generator Bldg 601 | Gulkana Airport Building 601, Glennallen, AK 99588 | Lat: 62.158340; Long: -145.462433 | Approx 15 cy | Several diesel generators and AST | Gretchen Caudill |  | 5/15/2018: Report or Workplan Review-other | Active
FAA Gulkana Bldg 102 Heating Oil UST 32-D-003 | Gulkana Airport Building 102, Glennallen, AK 99588 | Lat: 62.157990; Long: -145.461316 | Approx 26 cy | 515 gal heating oil UST | Gretchen Caudill | Advance approval required to transport soil or groundwater off-site. | 4/26/2016: Update or other Action | Cleanup Complete
FAA Gulkana Water Treatment Bldgs 603/604 Fuel-Contaminated Soil Assoc w/ Decommissioned Well | Gulkana Airport Buildings 603/604, Glennallen, AK 99588 | Lat: 62.157845; Long: -145.461799 | Aprox 7 cy | Spills from unknown source, former heating oil UST, vehicle maintenance activities |  | Advance approval required to transport soil or groundwater off-site. | 11/21/2012: Cleanup complete determination issued | Cleanup Complete
FAA Gulkana Bldg 600 | Gulkana Airport Building 600, Glennallen, AK 99588 | Lat: 62.157874; Long: -145.460327 | 178 cy | 2,000 gal heating oil AST, 515 gal diesel UST | Gretchen Caudill |  | 5/15/2018: Report or Workplan Review-other | Active
Eagle Air | Glennallen, AK 99588 | Lat: 62.157535; Long: -145.460054 |  | Avgas contamination |  | Advance approval required to transport soil or groundwater off-site. | 10/27/2006: Update or other Action | Cleanup Complete
FAA Gulkana Flight Service Station | Gulkana Airport; Flight Service Station Building, Glennallen, AK 99588 | Lat: 62.158162; Long: -145.457669 | 37.4 tons of soil | Lead-based paint |  | Movement or use of contaminated material (including on site) in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70). Advance approval required to transport soil or groundwater off site. | 11/27/2017: Cleanup complete determination issued | Cleanup Complete
FAA Gulkana Bldg 400 AST 32-D-005 | Gulkana Airport Building 400, Glennallen, AK 99588 | Lat: 62.158092; Long: -145.457295 | Approx 55 cy | heating oil AST, petroleum |  | Advance approval required to transport soil or groundwater off-site. | 11/21/2012: Cleanup complete determination issued | Cleanup Complete
FAA Gulkana Station-Sitewide | Gulkana Airport, Glennallen, AK 99588 | Lat; 62.156310; Long: -145.455229 |  | Numerous tanks and releases, 142 barrels of asphalt, petroleum staining | Gretchen Caudill |  | 2/2/2017: Site Characterization report approved | Informational
NPS Gulkana Airport | Gulkana Airport Lot 7 Block 21, Glennallen, AK 99588 | Lat: 62.155486; Long: -145.458801 | Approx 250 cy | Jet B fuel | IC Unit | Movement or use of contaminated material (including on site) in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70). Advance approval required to transport soil or groundwater off site. When contaminated soil is accessible, remediation should occur. Installation of groundwater wells requires ADEC approval. Every five years. | 4/12/2019: Institutional Control Compliance review | Cleanup Complete-Institutional Controls
ADOT&PF Gulkana Airport Blk 21 Lease Lots | Richardson Highway, 5 miles NE of Glennallen, Glennallen, AK 99588 | Lat: 62.155200; Long: -145.461100 |  | Three underground storage tanks (USTs); gasoline, diesel | Christy Howard |  | 4/30/2010: Update or other action: source area deleted from database because report determined area not contaminated | Informational
Gulkana Air Service | Lot 2A, BK 21, Gulkana Airport, Glennallen, AK 99588 | Lat: 62.155210; Long: -145.461490 |  | Three USTs; Jet fuel, avgas tank | IC Unit | Advance approval required to transport soil or groundwater off-site. Movement or useof cnotaminated material in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70). Copper Valley Air Services shall report to DEC every three years to document land use. New construction restrictions. Excavation/Soil movement restrictions. | 6/22/2018: Institutional control compliance review | Cleanup Complete-Institutional Controls
Ellis Air Taxi | Gulkana Airport, Richardson Hwy, Glennallen, AK 99588 | Lat: 62.155188; Long: -145.461944 |  |  |  | Advance approval required to transport soil or groundwater off-site. | 10/27/2006: Update or other action: file number issued. | Cleanup Complete
ADOTPF Gulkana Airport, Block 21, Lot 1A | 5 miles NE of Glennallen, Glennallen, AK 99588 | Lat: 62.155000; Long: -145.463000 | Approx 1,050 cy | fuel distribution area; two large above ground storage tanks; GRO, benzene, xylenes, DRO | Gretchen Caudill |  | 5/23/2019: Update or other action: request for update to DOT | Active
Gulkana Prepositioning Area & Army Site NALEMP | MP 117.3 Richardson Hwy, Gakona, AK 99586 | Lat: 62.143719; Long: -145.476651 | Approx 11 acres | abandoned 315,000 gal above ground storage tank, tires, food service unit, stove, water cooler, vehicle batteries, propane tanks, 5 gal paint buckets, several 55 gal drums | John O'Brien |  | 8/29/2019: Update or other action: transport request was approved. | Active
AMOCO Ahtna Inc. #1 | 14 Miles N of Glennallen, on Trans-Alaska Pipeline, Glennallen, AK 99588 | Lat: 62.122453; Long: -145.492673 |  | barium, chromium, lead |  | Advance approval required to transport soil or groundwater off-site. | 8/10/2006: Site closure approved | Cleanup Complete
Glennallen Quick Stop | Mile 115.5 Richardson Hwy, Glennallen, AK 99588 | Lat: 62.116803; Long: -145.477874 | Approx 4,800 sq ft | leaded gasoline | IC Unit | Notice of environmental contamination | 6/26/2019: Institutional control compliance review | Active
Hub of Alaska, Inc. | Glenn & Richardson Hwys; Mile 189.5 Glenn Hwy Glennallen, AK 99588 | Lat: 62.108292; Long: -145.477486 | Approx 600 cy | two 12,000 gal gas USTs; 12,000 gal diesel UST | Robert Weimer |  | 4/11/2019: Report or workplan review-other | Active
CVEA Glennallen Power Plant GW | Mile 187 Glenn Hwy, Glennallen, AK 99588 | Lat: 62.110315; Long: -145.532860 | Approx 600 cy | 1,000 gal gas UST, petroleum, diesel | Joshua Barsis |  | 5/20/2019: Report or workplan review-other | Active
Copper Valley Electric, Glennallen | Richardson Hwy, Glennallen, AK 99588 | Lat: 62.110799; Long: -145.533122 |  | gas UST |  | Advance approval required to transport soil or groundwater off-site. | 1/29/1994: Site closure approved | Cleanup Complete
Glennallen Fuel and Service Heating Oil UST | MP 187 Glenn Hwy Glennalle, AK 99588 | Lat: 62.107523; Long: -145.534883 | 600 gallons | 600 gal diesel | Robert Weimer |  | 8/8/2019: Exposure tracking model ranking | Active
R & J Enterprises | Mile 110.9 Richardson Hwy Glennallen, AK 99588 | Lat: 62.107648; Long: -145.535838 | Approx 75 cy |  |  | Advance approval required to transport soil or groundwater off-site. | 4/29/2008: Update or other action: file number assigned | Cleanup Complete
CVEA Glennallen Plant Mgr Residence | Mile 187 Glenn Hwy, CVEA Road, Glennallen, AK 99588 | Lat: 62.109282; Long: -145.538696 | Approx 300 gal | antifreeze |  | Advance approval required to transport soil or groundwater off-site. | 8/27/2001: Update or other action: notification letter | Cleanup Complete
ADF&G-Glenn Highway | MP 186.5 Glenn Hwy, Glennallen, AK 99588 | Lat: 62.108832; Long: -145.543129 | Approx 34 cy | 2,000 gal gas UST |  | Advance approval required to transport soil or groundwater off-site. | 5/54/2005: Site closure approved | Cleanup Complete
Glennallen Repeater Site | Mile 186 Glenn Hwy, Glennallen, AK 99588 | Lat: 62.109299; Long: -145.548074 |  | 2,000 gal gas tank; diesel, petroleum |  | Advance approval required to transport soil or groundwater off-site. | 10/27/2006: Update or other action: file number issued. | Cleanup Complete
Chevron-Glennallen | Glenn Hwy, Glennallen, AK 99588 | Lat: 62.109162; Long: -145.546387 |  | gasoline |  | Advance approval required to transport soil or groundwater off-site. | 10/31/2006: Update or other action: file number updated | Cleanup Complete
AT&T Alascom Glennallen Repeater | Mile 186 Glenn Hwy, Glennallen, AK 99588 | Lat: 62.110278; Long: -145.546944 | 2.5 acres | diesel |  | Advance approval required to transport soil or groundwater off-site. | 6/11/2008: Update or other action: added file number | Cleanup Complete
ADOT&PF Glenn Highway Maintenance Camp | Mile 185 Glenn Hwy, Glennallen, AK 99588 | Lat: 62.106944; Long: -145.547389 |  | asbestos, lead paint, gas, diesel, petroleum; 55 gal drums, refuse piles, two ASTs | Michael Hooper |  | 4/4/2019: Potentially responsible party/state interest letter | Active
CVEA Glennallen Tank Liner | Mile 187 Glenn Hwy, Glennallen, AK 99588 | Lat: 62.116199; Long: -145.552158 |  | Tank farm EPH contamination |  |  | 8/27/2001: Update or other action: notification letter | Cleanup Complete
Alyeska PS 11 Diesel Fuel Skid | Mile 114 Richardson Hwy, Pump Station 11, Glennallen, AK 99588 | Lat: 62.087000; Long: -145.480000 | 1 tank | 5000 gal diesel tank |  | Advance approval required to transport soil or groundwater off-site. | 4/21/1998: Site Ranked Using the AHRM | Cleanup Complete
Residence-629 Tazlina Terrace | 629 Tazlina Terrace, Copperville Alaska, Glennallen, AK 99588 | Lat: 62.064844; Long: -145.410740 | 2 tanks | heating oil AST and UST |  | Movement or use of contaminated material (including on site) in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70). Advance approval required to transport soil or groundwater off site. | 5/24/2017: Cleanup Complete Determination issued | Cleanup Complete
Tazlina Copper Valley School | Former Copper Valley School, in the village of Tazlina south of Glennalen, Glennallen, AK 99588 | Lat: 62.047510; Long: -145.403060 | 60 acres | asbestos, unknown powder and grandular substances, releases from heating oil tanks, various uncontrolled dumps, lead acid batteries, paint |  | Movement or use of contaminated material (including on site) in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70). Advance approval required to transport soil or groundwater off site. | 2/4/2015: Cleanup Complete Determination Issued | Cleanup Complete
Tazlina River Dumpsite | N Bank of Tazlina River; -0.2 mile SE of Tazlina Former Copper Valley School, Tazlina, -6 mile SE of Glennallen, Glennallen, AK 99588 | Lat: 62.044612; Long: -145.401485 | 0.15 acres | dumpsite-residential refuse, construction debris, batteries, piping, drums, other metals, arsenic | John Carnahan | Notice of environmental contamination. Advance approval required to transport soil or groundwater off-site. Period reivew: report to DEC every 5 years. | 2/4/2015: Institutional Control Record established | Cleanup Complete-Institutional Controls
ADOTPF-Tazlina Maintenance Station | Mi 110 Richardson Hwy, Glennallen, AK 99588 | Lat: 62.044059; Long: -145.424946 | Approx 2,000 cy | 8000 gal diesel UST, 8000 gal gas UST | IC Unit | CS Database Notation and letter to landowner/RP. When contaminated soil is accessible, remediation should occur. Advance approval required to transport soil or groundwater off-site. Movement or use of contaminated material in a manner that results in violation of the water quality standards is prohibited. Period review: 5 years. | 6/18/2018: Institutional Control Compliance Review | Cleanup Complete-Institutional Controls
ADOT&PF Tazlina Maintenance Station Class V Injection Well | Mile 110 Richardson Hwy, Glennallen, AK 99588 | Lat: 62.044084; Long: -145.425712 |  | polycyclic aromatic hydrocarbon analytes, VOCs | Michael Hooper |  | 9/26/2019: Report or workplan review-other: approved workplan for site characterization | Active
Old BIA Copper Center School | Old Richardson Hwy, Approx 0.6 miles SE of Subdivision Road, Copper Center, AK 99573 | Lat: 61.972317; Long: -145.319573 |  | asbestos, petroleum | Gretchen Caudill |  | 6/28/2019: Update or other action: letter to BIA to request meeting to discuss planning for cleanup. | Active
Copper Center Mountain View Gas & Liquor | Mile 100.8 Old Richardson Hwy, Copper Center, AK 99573 | Lat: 61.953975; Long: -145.305900 | 2 USTs | gas, benzene, toluene, ethylbenzene, diesel | Joshua Barsis |  | 2/26/2018: Update or other action: compliance letter sent | Active
AT&T Alascom TAPS Repeater Stuck | 25 miles S, SE of Glennallen, On hill overlooking Copper River Valley, Glennallen, AK 99588 | Lat: 61.790819; Long: -145.256078 | AST | petroleum | IC Unit | Advance approval required to transport soil or groundwater off-site. | 12/14/2011: Institutional Control record removed | Cleanup Complete
Vehicle Rollover MP 83.5 Richardson Highway | MP 83.5 Richardson Hwy, 17.5 miles South of Copper Center, Copper Center, Ak 99573 | Lat: 61.720842; Long: -145.163182 | 250 gal | 14,144 gal diesel, antifreeze, power steering fluid |  | Movement or use of contaminated material (including on site) in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70). Advance approval required to transport soil or groundwater off site. | 3/27/2015: Cleanup Complete Determination Issued | Cleanup Complete
Kenny Lake Mercantile | Mile 7.5 Edgerton Hwy, Copper Center, AK 99573 | Lat: 61.736303; Long: -144.945505 | UST |  |  | Advance approval required to transport soil or groundwater off-site. | 1/20/2006: Update or other action: saw letter of no further action | Cleanup Complete
ADOTPF-Chitina Maintenance Station | Mi 33 Edgerton Hwy, Chitina, AK 99566 | Lat: 61.582000; Long: -144.435300 | Approx 180 cy | 2500 gal diesel tank, 2500 gas tank | IC Unit | Advance approval required to transport soil or groundwater off-site. | 9/26/2012: Institutional Control Record Removed | Cleanup Complete
Trading Post Café / Chitina Saloon | MP 33.3, Edgerton Hwy, Chitina, AK 99566 | Lat: 61.516702; Long: -144.437226 |  | diesel | Randy Guintu |  | 9/19/2014: Update or other action; follow up regarding actions required | Active
Strelna Roadhouse | Mile 15 McCarthy Road, Chitina, AK 99566 | Lat: 61.515354; Long: -144.439083 |  | petroleum hydrocarbons | IC Unit | Notice of environmental contamination. Advance approval required to transport soil or groundwater off-site. | 1/13/2015: Institutional Control update | Cleanup Complete-Institutional Controls
Chitina Power Plant | Upper Village Road Jct, with Lower Village Road, Chitina, AK 99566 | Lat: 61.510221; Long: -144.451257 | Approx 200 cy | 1500 gal diesel | Randy Guintu |  | 11/14/2019: Update or other action: emailed overdue report letter | Active
ADOT&PF Nelchina Maintenance Station Class V Injection Well | Mile 142.5 Glenn Highway, Glennallen, AK 99588 | Lat: 61.982835; Long: -146.841531 |  | one injection well | Michael Hooper |  | 6/13/2019: Meeting or teleconference held | Active
Eureka Lodge | MP 128 Glenn Highway; -30 miles W of Glennallen, Glennallen, AK 99588 | Lat: 61.938190; Long: -147.172120 | 20 gals | premium unleaded gas, diesel range organics, benzene, ethylbenzene, xylenes, heating oil | Grant Lidren |  | 8/27/2019: Site visit | Active
ADOTPF-Paxson Maintenance Station | Mi 185.5 Richardson Hwy, Glennallen, AK 99588 | Lat: 63.033920; Long: -145.495527 | Approx 50 cy | diesel, gasoline, used oil | IC Unit | Excavation/Soil Movement Restrictions. Periodic Review: check with RP every three years. Advance approval required to transport soil or groundwater off site. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. Groundwater Use Restrictions: ADEC must be notified prior to installation of groundwater wells. | 11/23/2016: Institutional Control Update: follow up on land use every three years. | Cleanup Complete-Institutional Controls
FAA Gulkana | Mile 120 Richardson Hwy, Glennallen, AK 99588 | Lat: 62.159442; Long: -146.455413 |  | gasoline |  | Advance approval required to transport soil or groundwater off site. | 11/21/2012: Cleanup complete determination issued | Cleanup Complete
Former Lake Louise Convenience Store | Mile 160 Glenn Highway, Glennallen, AK 99588 | Lat: 62.087333; Long: -146.352310 |  | gas USTs, benzene |  | Advance approval required to transport soil or groundwater off site. | 6/10/2009: Leaking Underground Storage Tank Cleanup Initiated-petroleum | Cleanup Complete
Send International Maintenance Shop | Mile 187 Glenn Highway; Corner of College Rd and Drum Dr, Glennallen, AK 99588 | Lat: 61.111000; Long: -145.540000 |  | USTs 1 & 2, petroleum |  | Advance approval required to transport soil or groundwater off site. | 4/29/2009: Leaking Underground Storage Tank Cleanup Initiated-Petroleum | Cleanup Complete
ADOTPF-Nelchina Maintenance Station | Mile 142.5 Glenn Highway, Glennallen, AK 99588 | Lat: 62.102525; Long: -147.152960 |  | waste oil |  | Advance approval required to transport soil or groundwater off site. | 7/21/2008: Update or other action: file number given | Cleanup Complete
ADOTPF-Nelchina Maintenance Station | Mile 142.5 Glenn Highway, Glennallen, AK 99588 | Lat: 61.982300; Long: -146.840100 | Approx 60 cy | gasoline, diesel, used oil |  | Advance approval required to transport soil or groundwater off site. | 6/23/2004: Site Closure Approved | Cleanup Complete
Lake Louise Army Training Camp | 19.3 Mile Lake Louise Rd, Off Mile 159.8 Glenn Hwy, Glennallen, AK 99588 | Lat: 62.283889; Long: -146.525833 |  | mess hall remains and foundation, quonset hut remains, three latrines, the Marston landing mat/railroad tie breakwater and dock, barrck pads, property line fencing and posts and other visible debris |  |  | 2/6/2013: Final Cleanup Report Reviewed | Cleanup Complete
Alyeska PS 11 Block Valve 20 BL2 | Mile 114 Richardson Hwy, Pump Station 11, Glennallen, AK 99588 | Lat: 62.087000; Long: -145.480000 | 5 gals | diesel |  | Advance approval required to transport soil or groundwater off site. | 2/4/2004: Site Closure Approved | Cleanup Complete
AT&T Alascom TAPS Repeater Kimball Pass | 45 miles S, SE of Glennallen, Glennallen, AK 99588 | Lat: 61.512222; Long: -145.026667 |  | petroleum | IC Unit | Advance approval required to transport soil or groundwater off site. When contaminated soil is accessible, remediation should occur. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. | 8/15/2019: Institutional Control Compliance Review | Cleanup Complete-Institutional Controls
AT&T Alascom TAPS Repeater Round Top | 60 Miles N of Glennallen, Glennallen, AK 99588 | Lat: 62.803825; Long: -145.317842 |  | petroleum | IC Unit | Advance approval required to transport soil or groundwater off site. When contaminated soil is accessible, remediation should occur. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. | 8/1/2019: Instituional Control Compliance Review | Cleanup Complete-Institutional Controls
Tazlina River Trading Post | Mile 111.2 Richardson Hwy in Tazlina, Glennallen, AK 99588 | Lat: 62.063873; Long: -146.454712 | 1,000 cy | extensive hydrocarbon, benzene |  | Advance approval required to transport soil or groundwater off site. | 11/3/2004: Update or other action: file number issued | Cleanup Complete
Lake Louise Air Force Rec Camp | Former AF Rec Camp, End of Lake Louise Access, Glennallen, AK 99588 | Lat: 62.301163; Long: -146.590590 | 25 acres | diesel, building debris, concrete slabs and perimeter foundations | Kevin Fraley |  | 10/23/2019: Report or Workplan Review-Other: DEC approved final work plan | Active
CVEA Glennallen Ethylene Glycol | Mile 187 Glenn Highway, Glennallen, AK 99588 | Lat: 62.109282; Long: -145.538696 | Approx 3 cy | ethylene glycol |  | Advance approval required to transport soil or groundwater off site. | 8/27/2001: Update or other action: notification letter | Cleanup Complete
Sourdough Roadhouse | MP 147.5 Richardson Hwy, Gakona, AK 99586 | Lat: 62.529080; Long: -145.517000 |  | benzene |  | Advance approval required to transport soil or groundwater off site. | 5/11/2006: Site Closure Approved | Cleanup Complete
Alyeska PLMP 734 Pipe Leak | Mile 65 Richardson Hwy, Pipeline Mile 734, Copper Center, AK 99573 | Lat: 61.487228; Long: -145.156862 | Approx 100 cy | crude oil | IC Unit | Advance approval required to transport soil or groundwater off site. Required every five years. When contaminated soil is accessible, remediation should occur. Instalation of groundwater wells will require approval from ADEC. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. | 6/12/2017: Institutional Control Periodic Reporting | Cleanup Complete-Institutional Controls
Alyeska PS 12 Mainline Turbine Sump | Mile 64.7 Richardson Hwy, Pipeline Mile 735 Copper Center, AK 99573 | Lat: 61.476054; Long: -145.145558 | 30 gals | MLT sump, petroleum, turbine fuel | IC Unit | Advance approval required to transport soil or groundwater off site. When contaminated soil is accessible, remediation should occur. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. Alyeska shall report to DEC every five years to document land use. | 6/19/2018: Institutional Control Compliance Review | Cleanup Complete-Institutional Controls
Alyeska PS 12 Fuel Island Area | Mile 64.7 Richardson Hwy, Pipeline Mile 735 Copper Center, AK 99573 | Lat: 61.475900; Long: -145.145300 |  | turbine fuel, diesel |  | Advance approval required to transport soil or groundwater off site. | 5/2/2013: Cleanup Complete Determination Issued | Cleanup Complete
Powerhouse Fuel Tank Farm | Kennicott, McCarthy, Chitina, AK 99566 | Lat: 61.486380; Long: -142.886390 | Approx 79,000 sq ft | leaking tank and other unknown sources |  | Advance approval required to transport soil or groundwater off site. | 3/10/1995: Update or other action: remedial action report review | Cleanup Complete
NPS Kennicott Mine | Kennicott, McCarthy, Chitina, AK 99566 | Lat: 61.484650; Long: -142.887750 | Approx 300 sq ft | transformer oil, lube oil/grease | Gretchen Caudill |  | 3/11/2019: Update or other action: PA received from NPS | Active
NPS Kennicott Mine Monroe Tank 4(1) | Kennicott, McCarthy, Chitina, AK 99566 | Lat: 61.487903; Long: -142.890195 |  | petroleum | Gretchen Caudill |  | 3/11/2019: Update or other action: PA received from NPS | Active
NPS Kennicott Mine Lead Paint | Kennicott, McCarthy, Chitina, AK 99566 | Lat: 61.484680; Long: -142.887880 |  | lead | Gretchen Caudill |  | 3/11/2019: Update or other action: PA received from NPS | Active
ADOTPF-O'Brien Creek, UL T-235-2A | O'Brien Creek; Mile 113 Taylor HWY, Chitina, AK 99566 | Lat: 64.316828; Long: -141.418246 | Approx 160 cy | diesel, unleaded gas, used oil, arsenic | IC Unit | Groundwater use restrictions. Advance approval required to transport soil or groundwater off site. When contaminated soil is accessible, remediation should occur. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. Review of site conditions every three years. | 6/20/2018: Institutional Control Compliance Review | Cleanup Complete-Institutional Controls
FAA Summit NDB/RCO | Mile 201 Parks Highway, -9 mile S of Cantwel, Cantwell, AK 99729 | Lat: 63.331035; Long: -149.129614 | Approx 800 cy | petroleum hydrocarbon, diesel, gas | John O'Brien |  | 2/6/2017: Meeting or teleconference held | Active
FAA Summit Former Tank Farm | Mile 201 Parks Highway, -9 mile S of Cantwel, Cantwell, AK 99729 | Lat: 63.331035; Long: -149.129614 |  | petroleum | John O'Brien |  | 2/6/2017: Meeting or teleconference held: discuss next steps for closure. | Active
FAA Summit Flight Service Station | Mile 201 Parks Highway, -9 mile S of Cantwel, Cantwell, AK 99729 | Lat: 63.331035; Long: -149.129614 | Approx 7,000 gals | diesel, asbestos, PCBs, debris | John O'Brien |  | 2/6/2017: Meeting or teleconference held: discuss next steps for closure. | Active
FAA Summit Radio Range | Mile 201 Parks Highway, -9 mile S of Cantwel, Cantwell, AK 99729 | Lat; 63.313569; Long: -149.189787 | Approx 70 cy | petroleum hydrocarbon, chlorinated herbicide 2, 4-D, 5-T, diesel |  | Advance approval required to transport soil or groundwater off site. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. | 6/19/2019: Update or other action: site location updated | Cleanup Complete
Valdez Creek Mine-Waste Motor Oil | Denali Highway, Cantwell, AK 99729 | Lat: 63.103947; Long: -147.539772 | Approx 50,000 gals | waste motor oil |  | Advance approval required to transport soil or groundwater off site. | 5/21/1990: Site closure approved | Cleanup Complete
FAA Summit Air Navigation Site-Sitewide | Mile 201 Parks Highway, Quarters & Service Area, Cantwell, AK 99729 | Lat: 63.331035; Long: -149.129614 | Approx 2 acres | diesel, diesel, gas | John O'Brien |  | 2/6/2017: Meeting or teleconference held: discuss next steps for closure. | Active
Valdez Creek Mine-Collective Areas | Denali Highway, Cantwell, AK 99729 | Lat: 63.103947; Long: -147.539772 | Approx 5,000 gals | diesel, waste oil, antifreeze |  | Advance approval required to transport soil or groundwater off site. | 2/24/2004: Update or other action: file number assigned. | Cleanup Complete
Valdez Creek Mine-Dam Blow-Out | Denali Highway, Cantwell, AK 99729 | Lat: 63.106189; Long: 147.526800 | Approx 60 million gals | water reservoir carrying mining tailings-metals, turbidity, settable solids |  | Advance approval required to transport soil or groundwater off site. | 5/25/1995: Site Number Identifier Changed | Cleanup Complete
Drashner Homestead | Mile 131 Denali Highway, Cantwell, AK 99729 | Lat: 63.371748; Long: -148.829816 |  | diesel | Shawn Tisdell |  | 4/9/2019: Update or other action: DEC send correspondence requesting site visit | Active
AT&T Alascom Honolulu Repeater | Mile 180 Parks Highway, Cantwell, AK 99729 | Lat: 63.094722; Long: -149.505278 |  | diesel |  | Advance approval required to transport soil or groundwater off site. | 11/26/2001: Site Closure Approved | Cleanup Complete
AT&T Alascom Cantwell Repeater | 1.5 Mile W of Airport, Cantwell, AK 99729 | Lat: 63.401111; Long: -148.937778 |  | diesel |  | Advance approval required to transport soil or groundwater off site. | 12/27/2000: Site Closure Approved | Cleanup Complete
ARRC Summit Siding | ARRC Mile Post 312.5, Near Summit Lake, Cantwell, AK 99729 | Lat: 63.327396; Long: -149.126229 | Approx 20 cy | weathered gasoline and diesel | Grant Lidren |  | 1/26/2011: Update or other action: no work was ever performed. | Active
USPS Cantwell Post Office | Mile 210 George Parks Hwy, 0.1 Mi N of Denali Hwy, Cantwell, AK 99729 | Lat: 63.391885; Long: -148.901105 | Approx 150 cy | diesel, heating oil | Jamie McKellar |  | 8/15/2019: Site visit | Active
ARRC Cantwell Section House | Intersection Denali Hwy, and railroad mainline, Cantwell, AK 99729 | Lat: 63.391147; Long: -148.952697 |  | potential contaminated concentrations | IC Unit | Advance approval required to transport soil or groundwater off site. | 7/9/2012: Institutional Control Record Review | Cleanup Complete
ADOTPF-Cantwell Maintenance Station | Mile 135 Denalie Highway, Cantwell, AK 99729 | Lat: 63.388998; Long: -148.885004 | Approx 75 cy | used oil, diesel, gas, benzene | IC Unit | Advance approval required to transport soil or groundwater off site. | 12/14/2011: Institutional Control record removed | Cleanup Complete
ARRC-Broad Pass Railroad Station | Mile 304.5 Alaska Railrd; MP 193 Parks Highway, Cantwell, AK 99729 | Lat: 63.235438; Long: -149.268617 | 1/2 acre | diesel | IC Unit | Advance approval required to transport soil or groundwater off site. Excavation/Soil movement restrictions. | 4/14/2015: Institutional Control Update: no change in land ownership or use | Cleanup Complete-Institutional Controls
ADOTPF-Chulitna Wayside | MP 185.5 Parks Hwy, Cantwell, AK 99729 | Lat: 63.151518; Long: -149.410605 | one UST | diesel, gas, benzene |  | Advance approval required to transport soil or groundwater off site. | 5/16/2005: Site Closure Approved | Cleanup Complete
Tesoro-Tsesyu-Parks Hwy. | Mile 210 Parks Hwy; Denali Hwy, Cantwell, AK 99729 | Lat: 63.389897; Long: -148.903642 | two USTs | unleaded gas, diesel, benzene, toluene, ethyl benzene, xylene |  | Advance approval required to transport soil or groundwater off site. | 2/11/1997: Site Closure Approved | Cleanup Complete
ARRC-Cantwell Station | ARR mile 319.5 Cantwell, AK 99729 | Lat: 63.391200; Long: -148.953090 | UST | petroleum |  | Advance approval required to transport soil or groundwater off site. | 6/11/1996: Site Closure Approved | Cleanup Complete
Reindeer Mountain Lodge | Mile 209 Geo Parks Hwy Lot 25 B- C & D Cantwell Small Tracts, Cantwell, AK 99729 | Lat: 63.387049; Long: -148.904912 | Approx 45 cy | reg and unleaded gasoline | IC Unit | Advance approval required to transport soil or groundwater off site. | 12/5/2014: Update or Other Action: drinking water well sampling showed non-detect concentrations | Cleanup Complete
ADOTPF-East Fork Maintenance Station | MP 185 Parks Hwy Cantwell, AK 99729 | Lat: 63.144200; Long: -149.424200 | Approx 700 cy | diesel, gasoline, used oil, benzene | IC Unit | Advance approval required to transport soil or groundwater off site. Groundwater use restrictions. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. Periodic review-every three years. | 6/20/2018: Institutional Control Compliance Review | Cleanup Complete-Institutional Controls
ARRC Broad Pass Railroad Station | MP 193 Parks Highway; ARRC MP 304.5; -15 m SW of Cantwell, Cantwell, AK 99729 | Lat: 63.235530; Long: -149.268670 | one UST | diesel heating oil | IC Unit | Advance approval required to transport soil or groundwater off site. | 1/13/2016: Institutional Control Update: property owner not changed | Cleanup Complete-Institutional Controls
Nenana Heating Services Truck Rollover-MP 134.5 Denali Highway | Milepost 134.5 Denali Highway, Cantwell, AK 99729 | Lat: 63.392324; Long: -148.913708 | 260 gals | ultra low sulfur #1 diesel fuel |  | Advance approval required to transport soil or groundwater off site. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. | 5/5/2017: Cleanup Complete Determination Issued | Cleanup Complete
ADOT&PF Cantwell Maintenance Station Class V Injection Well | Milepost 135 Denali Highway Cantwell, AK 99729 | Lat: 63.389141; Long: -148.884484 | underground injection well | metals, VOCs, SVOCs | Michael Hooper |  | 7/19/2018: Report or Workplan Review-other: EPA approval of closure plan | Active
Lynden Transport Vehicle Accident-MP 169 Parks Highway | MP 169 Parks Highway; ARRC MP 279.6 Crossing; -41 m S of Cantwell, Cantwell, AK 99729 | Lat: 62.952536; Long: -149.657994 | Approx 200 gals | diesel, petroleum |  | Advance approval required to transport soil or groundwater off site. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. | 5/20/2016: Institutional Control Record Removed | Cleanup Complete
FAA Summit Former Housing South | Mile 201 Parks Highway Cantwell, AK 99729 | Lat: 63.327011; Long: -149.132119 |  | petroleum, diesel, polycyclic aromatic hydrocarbons | John O'Brien |  | 2/6/2017: Meeting or teleconference held: discuss next steps for closure. | Active
FAA Summit Former Housing North | Mile 201 Parks Highway Cantwell, AK 99729 | Lat: 63.327500; Long: -149.134192 |  | petroleum, gas, diesel, polycyclic aromatic hydrocarbons |  | Advance approval required to transport soil or groundwater off site. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. | 7/3/2018: Cleanup Complete Determination Issued | Cleanup Complete
FAA Summit Former Gasoline Pumphouse and AST | Mile 201 Parks Highway Cantwell, AK 99729 | Lat: 63.328442; Long: -149.134136 | AST | gas, diesel, benzene, ethylbenzene, polycyclic aromatic hydrocarbons | John O'Brien |  | 2/6/2017: Meeting or teleconference held: discuss next steps for closure. | Active
Igloo City USTs | Mile 188.5 Parks Highway; -19.5 m SW of Cantwell, Cantwell, AK 99729 | Lat: 63.188040; Long: -149.359925 | Approx 100 cy | petroleum, gas, diesel | Bill O'Connell |  | 8/1/2018: Leaking Underground Storage Tank Cleanup Initiated-Petroleum | Active
Former Tazlina Copper Valley School | Tazlina Village Hall, Glennallen, AK 99588 | Lat: 62.1987; Long: -146.05 | 30 acres
Copper Valley School (Former) | Old School Road, Tazlina, AK 99588 | Lat: 62.0482037; Long: -145.409791 | 15 acres