## CRNA Public Record
Copper Rive Native Association Tribal Health Consortia
Tribal Response Program (TRP) Public Record
Site Name | Location | Coordinates | Landowner | Current Use | Contacts/Staff | Size | Contaminates | Institutional Controls | Action Information | Planned Actions
Old BIA Copper Center School | Old Richardson Highway, 1.3 miles N/NW of Copper Center, AK | Lat: 61.972317; Long: -145.319573 | AK DNR | Abandoned BIA school | Copper River Native Association, Native Village of Klui-Kaah, AK Department of Natural Resources, AK Department of Environmental Conservation | 4,788 sq ft | Water outfall piping, partially buried 55-gal drum, two utility connection points, former AST site, vertical pipe protruding from ground, large rectangular ditch; diesel, gas, BTEX, asbestos, lead based paint | Windows and doors boarded up to prevent access. | February 2024: CRNA received a full site assessment report from ERG. | In progress: planning full cleanup summer of 2025 with TRP funds
Airport Dump | End of Airport Road, Copper Center, AK | Lat: 61 55'56.09"; Long: -145 17'43.27" | University of Alaska | illegal dump | Copper River Native Association, Native Village of Kluti-Kaah, University of Alaska | 0.34 acres | paint, freon, pil, fuel, petroleum, car parts, tires, metal |  | January 2024: CRNA received a full site asssessment report from Nortech. | No actions planned.
Tazlina Old Laundromat | M 104 Old Richardson Highway, Copper Center, AK | Lat: 61 59'42.19"N; Long: -145 20'25.29"W | Ahtna, Inc. | abandoned laundromat facility | Copper River Native Association; Ahtna, Inc.; Native Village of Tazlina | approx 2 acres | Industrial water and chemicals and buried propane tanks and unknown |  | September 19, 2024: ChemTrack conducted collected soil and building materials samples for site assessment. | ChemTrack will develop final report of samples analysis and host community meeting to give findings report by November 2024.

## Other Public Record sites
Copper River Native Association Tribal Health Consortium
Tribal Response Program (TRP) Inventory List
Site Name | Location | Coordinates | Area | Contaminates | Contacts/Staff | Institutional Controls | Action Information | Status
Mentasta Traditional Council Building | 6 Mile Mentasta Lake Road, Mentasta Lake, AK 99780 | Lat: 62.930265; Long: -143.797735 |  | Multiple releases of arctic grade diesel (#1) fuel; aboveground storage tank (AST); heating oil AST | Michael Hooper |  | 7/19/2018: Spoke with RP on phone, they are going to contact EPA's IGAP program regarding funding | Active
Mentasta School | 6 Miles off the Tok Cutoff of the Glenn Highway, 38 miles south of Tok Junction, Mentasta Lake, AK 99780 | Lat: 62.929500; Long: -143.797800 |  | two 9,000 gallon diesel USTs spills and overfills; 19,000 ppm DRO contamination; 4,50 ppm DRO contamination | IC Unit | Monitoring of DW well required every other year. | 4/14/2023: IC compliance review completed and a reminder letter was issued to the Alaska Gateway School District on this date. | Cleanup Complete-Institutional Controls
Mentasta Village Clinic | PO Box 600, Mentasta Lake, AK 99780 | Lat: 62.902500; Long: -143.748090 | Approx 350 cy | 300 gal heating fuel tank | IC Unit | Advance approval required to transport soil or groundwater off-site. | 6/11/2012: This site meets the 2009 closure policy requirements therefore IC's can be removed. The default requirement of no offsite transport of soil and groundwater from this site will still apply. | Cleanup Complete
Mentasta Lodge | MP 78.1 Tok Cutoff Highway, Gakona, AK 99586 | Lat: 62.888757; Long: -143.678746 | Approx 175 cy | 1 5,000 gal unleaded gas UST and 1 1,000 gal diesel automotive fuel UST | IC Unit | Advance approval required to transport soil or groundwater off-site. | 7/9/2013: The conditions at this site meet the 2009 closure policy, therefore IC's can be removed. The default requirement of no offsite transport of soil or groundwater will still apply. In accordance with 18 AAC 78.276(f)(2), ADEC may require additional site assessment, monitoring, remediation, and other necessary action at this facility should new information become available that indicates contamination at this site may pose a threat to human health or the environment. | Cleanup Complete
FAA Slana Station | Mile 64.8 Tok Cutoff, Slana, AK 99586 | Lat: 62.724694; Long: -143.866556 |  | 1,000 gal regulated underground storage tank, 55 gal drum incinerator; former aboveground storage tank, fuel line utility chase with sides but no bottom | Bob Glascott | Advance approval required to transport soil or groundwater off-site. | 6/19/2003: Site closure approval | Cleanup Complete
Duffys Roadhouse | Mile 62.7 Tok Cutoff; SR Box 370, Gakona, AK 99586 | Lat: 62.724786; Long: -143.914464 | Approx 30 cy | 2 2,000 gal unleaded gas USTs |  | Advance approval required to transport soil or groundwater off-site. | 2/10/1997: CLOS; Closure letter issued. Comments: Rushe 3/3/97 preliminary closure ltr. By DEC at request of RP not accepted by buyer. Buyer wanted final ltr issued 2/10/97 describing in detail cleanup actions conducted. | Cleanup Complete
ADOTPF – Slana Maintenance Station | 60 Mile Tok Cutoff, then 1/2 mile down Nebesna Rd, Slana, AK 99586 | Lat: 62.708467; Long: -143.978826 | Approx 1,200 cy | One 2,000 gal diesel UST, one 8,000 gal diesel UST, two 2,000 gal gas USTs | IC Unit | Movement or use of contaminated material (including on site) in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70). Advance approval required to transport soil or groundwater off site. | 8/8/2023: IC compliance review conducted with the help of a site visit/inspection by the Copper River Native Association representative. The property is still operated as a ADOT maintenance station. Vegetation on the property is healthy looking and the ground looks undisturbed other than vehicle tracks. | Cleanup Complete-Institutional Controls
ADOT&PF Slana Maintenance Station Class V Injection Well | 60 Mile Tok Cutoff, then 1/2 mile down Nebesna Rd, Slana, AK 99586 | Lat: 62.707519; Long: -143.978239 |  | Three injection wells | Michael Hooper |  | 12/8/2020: Site closure approved by EPMII. All contamination was removed from 2 of 3 injection wells. Minor soil contamination remaining under IW-6 is not expected to impact ground water. | Cleanup Complete
High Frequency Active Auroral Research Program (HAARP) | MP 11.3 Tok Cutoff, Gakona, AK 9986 | Lat: 62.391177; Long: -145.131447 | Approx 3 cy | Spill-two diesel generators | John Halverson | Advance approval required to transport soil or groundwater off-site. | 1/29/2015: DEC received and filed a Memorandum for Record from the AF updating the Environmental Baseline Survey (EBS) by documenting regulatory closure of th "category 2 area" where DRO had been found at a low concentration (580 mg/kg) that was above the method 2 migration to groundwater cleanup level. As noted in the Nov 12, 2014 DEC letter, the migration to groundwater cleanup levels were determined to not apply at the site due to permafrost. | Cleanup Complete
Heinz Salvage Yard Gakona | MP 4.7 Tok Cutoff, Gakona, AK 99586 | Lat: 62.312873; Long: -145.217487 |  | Numerous junk vehicles, fuel, glycols, oil, break fluid, gear lube, transmission fluid, batteries, storage tanks, drums | Lisa Griswold |  | 11/23/2021: ADEC reviewed the October 29, 2021 letter report for the drum and hazardous materials disposal documented in the June 30, 2021 Site Characterization Report. US Ecology removed eight 55 gallon drums on June 29, 2021, that were then consolidated and shipped to Tacoma, WA to be disposed of as hazardous waste. Three drums containing non-hazardous waste (noted at 9, 10, and 11 in the Site Characterization Report) could not be relocated and are presumed to have been removed. This submittal fulfills the request for a disposal confirmation from ADEC's July 29, 2021 letter. | Active
Gulkana NALEMP | MP 127.5 Richardson HWY, Gakona, AK 99586 | Lat: 62.273547; Long: -145.387219 | 6ft x 8ft x 4ft | Contained oil and diesel fuel | John O'Brien |  | 3/23/2023: DEC completed review and approved the Soil/Debris Removal and Site Investigation Report for the North Bluff Dumpsite and Former Wood-Cribbed Well/Sump Area sites. This report detailed the debris and soil removal conducted during the 2022 field season. Additional excavation and debris removal was conducted at the North Bluff Dumpsite area, including the temporary stockpiling and confirmation sampling of associated soils at Soil Stockpile No. 4. Soil removal and site investigation activities was conducted at the former Wood-Cribbed Well/Sump Area. Additional soil removal will be conducted in 2023 at the Former Wood-Cribbed Well/Sump Area. | Active
Gulkana Prepositioning Area & Army Site FUDS | N of Jct of Glenn & Richardson Hwys, N & NE, and S of Gulkana Airport, Gakona, AK 9586 | Lat: 62.273547; Long: -145.387219 | 5,044 ac | 3 full drums | John O'Brien |  | 2/6/2023: DEC completed review and approved the Preliminary Assessment for the FUDS Gulkana Prepositioning Area and US Army Site and Gulkana Staging Field. This document presented the findings obtained through research at various archives and records facilities to determine presence of hazardous substances as a result of previous use, storage, and/or disposal at the site. Based on the information provided in this document and information from other projects on the same property, there is evidence of contamination from former military use and activities. Debris has been observed throughout the property, in addition to surface and subsurface soil contamination from past fuel storage practices. DEC concurs with the conclusion that possible hazards remain at the Motor Pool, Motor Shed, and Ordinance Warehouse and should be investigated. | Active
FAA Gulkana Former Diesel AST Tank Farm | Gulkana Airport, Adjacent to and beneath ADOT&PF Equipment Storage Bldg, Glennallen, AK 99588 | Lat: 62.159110; Long: -145.461651 | 6,282 cy | 6 large, vertical diesel ASTs in a diked area; petroleum | Debra Caillouet | Advance approval required to transport soil or groundwater off-site. | 11/21/2012: The 2006 Site investigation maximum DRO detected 4600 mg/kg at 5-7' bgs for tank 3 and 4520 mg/kg DRO for tank 4 at 15-17' bgs. Additional borings outside of the former tank farm did not find DRO above this levels. No recoverable groundwater was found. | Cleanup Complete
FAA Gulkana Bldg 303 | Gulkana Airport Building 303, Glennallen, AK 99588 | Lat: 62.158856; Long: -145.461571 | 4,385 cy | 1,000 gal heating oil UST, gas pump, former gas AST | Gretchen Caudill |  | 4/15/2021: Reviewed sampling report for landfarm at RCAG facility. ISM samples collected in 2020 show that all analytes are below the most stringent cleanup levels. ADEC Agrees that no further action is warranted for these soils. The RCAG Landspread has been added as a source area. | Active
ADOT&PF Gulkana Maintenance Station Class V Injection Well | Mile 118.1 Richardson Hwy, Glennallen, AK 99588 | Lat: 62.158778; Long: -145.460775 | 7.5ft x 38ft | Injection well | Michael Hooper |  | 1/17/2024: Annual Meeting Held with DOT to discuss plans for coming year at all NR UIC sites. | Active
FAA Gulkana Engine Generator Bldg 601 | Gulkana Airport Building 601, Glennallen, AK 99588 | Lat: 62.158340; Long: -145.462433 | Approx 15 cy | Several diesel generators and AST | Gretchen Caudill |  | 6/24/2020: Approved Report for Site investigation happening in 2018. Overall contamination at this site is below the risk based levels, sites recommended for closure pending groundwater determination. | Active
FAA Gulkana Bldg 102 Heating Oil UST 32-D-003 | Gulkana Airport Building 102, Glennallen, AK 99588 | Lat: 62.157990; Long: -145.461316 | Approx 26 cy | 515 gal heating oil UST | Gretchen Caudill | Advance approval required to transport soil or groundwater off-site. | 4/26/2016: Update or other Action | Cleanup Complete
FAA Gulkana Water Treatment Bldgs 603/604 Fuel-Contaminated Soil Assoc w/ Decommissioned Well | Gulkana Airport Buildings 603/604, Glennallen, AK 99588 | Lat: 62.157845; Long: -145.461799 | Aprox 7 cy | Spills from unknown source, former heating oil UST, vehicle maintenance activities |  | Advance approval required to transport soil or groundwater off-site. | 11/21/2012: Cleanup complete determination issued | Cleanup Complete
FAA Gulkana Bldg 600 | Gulkana Airport Building 600, Glennallen, AK 99588 | Lat: 62.157874; Long: -145.460327 | 178 cy | 2,000 gal heating oil AST, 515 gal diesel UST | Gretchen Caudill |  | 6/24/2020: Approved Report for Site investigation happening in 2018. Overall contamination at this site is below the risk based levels, sites recommended for closure pending groundwater determination. | Active
Eagle Air | Glennallen, AK 99588 | Lat: 62.157535; Long: -145.460054 |  | Avgas contamination |  | Advance approval required to transport soil or groundwater off-site. | 10/27/2006: Update or other Action | Cleanup Complete
FAA Gulkana Flight Service Station | Gulkana Airport; Flight Service Station Building, Glennallen, AK 99588 | Lat: 62.158162; Long: -145.457669 | 37.4 tons of soil | Lead-based paint |  | Movement or use of contaminated material (including on site) in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70). Advance approval required to transport soil or groundwater off site. | 11/27/2017: Cleanup complete determination issued | Cleanup Complete
FAA Gulkana Bldg 400 AST 32-D-005 | Gulkana Airport Building 400, Glennallen, AK 99588 | Lat: 62.158092; Long: -145.457295 | Approx 55 cy | heating oil AST, petroleum |  | Advance approval required to transport soil or groundwater off-site. | 11/21/2012: Cleanup complete determination issued | Cleanup Complete
FAA Gulkana Station-Sitewide | Gulkana Airport, Glennallen, AK 99588 | Lat; 62.156310; Long: -145.455229 |  | Numerous tanks and releases, 142 barrels of asphalt, petroleum staining | Gretchen Caudill |  | 2/2/2017: Site Characterization report approved | Informational
NPS Gulkana Airport | Gulkana Airport Lot 7 Block 21, Glennallen, AK 99588 | Lat: 62.155486; Long: -145.458801 | Approx 250 cy | Jet B fuel | IC Unit | Movement or use of contaminated material (including on site) in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70). Advance approval required to transport soil or groundwater off site. When contaminated soil is accessible, remediation should occur. Installation of groundwater wells requires ADEC approval. Every five years. | 6/14/2022: IC compliance review conducted and a site visit was performed by the Copper River Native Association. Field notes state that the tarmac is still in place and that this is an active airport. There has been no new construction. There is one active aboveground storage tank. The surrounding vegetation look healthy. | Cleanup Complete-Institutional Controls
ADOT&PF Gulkana Airport Blk 21 Lease Lots | Richardson Highway, 5 miles NE of Glennallen, Glennallen, AK 99588 | Lat: 62.155200; Long: -145.461100 |  | Three underground storage tanks (USTs); gasoline, diesel | Christy Howard |  | 9/27/2021: Staff assigned changed to "no longer assigned" as the site does not appear to have confirmed contamination. Site retains its "informational" status as it was originally addressed through ADEC's Reuse and Redevelopment Program. For further information, please contact ADEC Brownfields staff. | Informational
Gulkana Air Service | Lot 2A, BK 21, Gulkana Airport, Glennallen, AK 99588 | Lat: 62.155210; Long: -145.461490 |  | Three USTs; Jet fuel, avgas tank | IC Unit | Advance approval required to transport soil or groundwater off-site. Movement or useof cnotaminated material in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70). Copper Valley Air Services shall report to DEC every three years to document land use. New construction restrictions. Excavation/Soil movement restrictions. | 9/27/2021: Staff assigned changed to "no longer assigned" as the site does not appear to have confirmed contamination. Site retains its "informational" status as it was originally addressed through ADEC's Reuse and Redevelopment Program. For further information, please contact ADEC Brownfields staff. | Informational
Ellis Air Taxi | Gulkana Airport, Richardson Hwy, Glennallen, AK 99588 | Lat: 62.155188; Long: -145.461944 |  |  |  | Advance approval required to transport soil or groundwater off-site. | 10/27/2006: Update or other action: file number issued. | Cleanup Complete
ADOTPF Gulkana Airport, Block 21, Lot 1A | 5 miles NE of Glennallen, Glennallen, AK 99588 | Lat: 62.155000; Long: -145.463000 | Approx 1,050 cy | fuel distribution area; two large above ground storage tanks; GRO, benzene, xylenes, DRO | Gretchen Caudill |  | 5/23/2019: Update or other action: request for update to DOT | Active
Gulkana Prepositioning Area & Army Site NALEMP | MP 117.3 Richardson Hwy, Gakona, AK 99586 | Lat: 62.143719; Long: -145.476651 | Approx 11 acres | abandoned 315,000 gal above ground storage tank, tires, food service unit, stove, water cooler, vehicle batteries, propane tanks, 5 gal paint buckets, several 55 gal drums | John O'Brien |  | 8/10/2023: Site Visit: DEC staff traveled to the Gulkana Prepositioning Area and US Army Site to view status of debris removal and site investigation at the AST Impact Area and Debris Area No. 2. DEC staff discussed site status with USACE, NVT, and contractor personnel and discussed future sampling efforts planned in 2024. | Active
AMOCO Ahtna Inc. #1 | 14 Miles N of Glennallen, on Trans-Alaska Pipeline, Glennallen, AK 99588 | Lat: 62.122453; Long: -145.492673 |  | barium, chromium, lead |  | Advance approval required to transport soil or groundwater off-site. | 8/10/2006: Site closure approved | Cleanup Complete
Glennallen Quick Stop | Mile 115.5 Richardson Hwy, Glennallen, AK 99588 | Lat: 62.116803; Long: -145.477874 | Approx 4,800 sq ft | leaded gasoline | IC Unit | Notice of environmental contamination | 5/27/2022: Institutional Control Update: E-mailed a reminder NEC Letter to the responsible party. | Active
Hub of Alaska, Inc. | Glenn & Richardson Hwys; Mile 189.5 Glenn Hwy Glennallen, AK 99588 | Lat: 62.108292; Long: -145.477486 | Approx 600 cy | two 12,000 gal gas USTs; 12,000 gal diesel UST | Robert Weimer |  | 7/31/2023: Document, Report, or Work plan Review-other: DEC reviewed the 2022 Site Characterization Report submitted to our office February 27, 2023. Comments were sent with several required site characterization efforts to be completed in the coming sample effort. Continued efforts need to be made to further delineate the contamination remaining in soil and groudwater. Additional monitoring wells must be installed to determine the extents of groundwater contamination downgradient of the previous underground storage tank area, dispenser island, and piping runs. A monitoring well should be located close to the non-potable water well. Because of remaining contaminants in the soil that are considered volatile, DEC is requiring a vapor intrusion study of the building. The log describing the water sample effort described the purged water as having a septic odor and was an odd color. DEC is requesting an effort to determine where the septic lines are located on the site. DEC also requested a well survey for horizontal and vertical locations of wells and continue to determine groundwater flow direction as the groundwater was substantially higher in September 2022 versus the April 2021 effort, and the flow direction had changed from east to south-southwest. | Active
CVEA Glennallen Power Plant GW | Mile 187 Glenn Hwy, Glennallen, AK 99588 | Lat: 62.110315; Long: -145.532860 | Approx 600 cy | 1,000 gal gas UST, petroleum, diesel | Joshua Barsis |  | 10/26/2023: Site Characterization Workplan Approved: A work plan was approved to conduct groundwater monitoring at wells GMW12, GMW16, GMW11, GMW15, and GMW10. A sample from the drinking water well on site will also be collected. All samples will be analyzed for DRO. | Active
Copper Valley Electric, Glennallen | Richardson Hwy, Glennallen, AK 99588 | Lat: 62.110799; Long: -145.533122 |  | gas UST |  | Advance approval required to transport soil or groundwater off-site. | 1/29/1994: Site closure approved | Cleanup Complete
Glennallen Fuel and Service Heating Oil UST | MP 187 Glenn Hwy Glennalle, AK 99588 | Lat: 62.107523; Long: -145.534883 | 600 gallons | 600 gal diesel | Robert Weimer |  | 6/1/2023: Document, Report, or Work plan Review-other: Reviewed the site characterization reports for both of these sites and issued an approval for both in one letter to the RP. DEC requested determination of groundwater flow direction and an additional sample effort of the tap water from the bathroom facilities to confirm the non-detect resulting from a 2021 sample that was biased low. Requested a groundwater investigation downgradient from the UST excavation area, with seasonal sample efforts that might become quarterly to determine seasonal trends in contaminant spread. Also requested information about soils used to backfill excavation pit because of sample results indicating contaminants above cleanup levels in those soils. | Active
R & J Enterprises | Mile 110.9 Richardson Hwy Glennallen, AK 99588 | Lat: 62.107648; Long: -145.535838 | Approx 75 cy |  |  | Advance approval required to transport soil or groundwater off-site. | 4/29/2008: Update or other action: file number assigned | Cleanup Complete
CVEA Glennallen Plant Mgr Residence | Mile 187 Glenn Hwy, CVEA Road, Glennallen, AK 99588 | Lat: 62.109282; Long: -145.538696 | Approx 300 gal | antifreeze |  | Advance approval required to transport soil or groundwater off-site. | 8/27/2001: Update or other action: notification letter | Cleanup Complete
ADF&G-Glenn Highway | MP 186.5 Glenn Hwy, Glennallen, AK 99588 | Lat: 62.108832; Long: -145.543129 | Approx 34 cy | 2,000 gal gas UST |  | Advance approval required to transport soil or groundwater off-site. | 5/54/2005: Site closure approved | Cleanup Complete
Glennallen Repeater Site | Mile 186 Glenn Hwy, Glennallen, AK 99588 | Lat: 62.109299; Long: -145.548074 |  | 2,000 gal gas tank; diesel, petroleum |  | Advance approval required to transport soil or groundwater off-site. | 10/27/2006: Update or other action: file number issued. | Cleanup Complete
Chevron-Glennallen | Glenn Hwy, Glennallen, AK 99588 | Lat: 62.109162; Long: -145.546387 |  | gasoline |  | Advance approval required to transport soil or groundwater off-site. | 10/31/2006: Update or other action: file number updated | Cleanup Complete
AT&T Alascom Glennallen Repeater | Mile 186 Glenn Hwy, Glennallen, AK 99588 | Lat: 62.110278; Long: -145.546944 | 2.5 acres | diesel |  | Advance approval required to transport soil or groundwater off-site. | 6/11/2008: Update or other action: added file number | Cleanup Complete
ADOT&PF Glenn Highway Maintenance Camp | Mile 185 Glenn Hwy, Glennallen, AK 99588 | Lat: 62.106944; Long: -145.547389 |  | asbestos, lead paint, gas, diesel, petroleum; 55 gal drums, refuse piles, two ASTs | Michael Hooper |  | 3/2/2020: Update or Other Action: Brownfield file 240.57.001 consolidated with file # 240.38.010 on this date. | Active
CVEA Glennallen Tank Liner | Mile 187 Glenn Hwy, Glennallen, AK 99588 | Lat: 62.116199; Long: -145.552158 |  | Tank farm EPH contamination |  |  | 8/27/2001: Update or other action: notification letter | Cleanup Complete
Alyeska PS 11 Diesel Fuel Skid | Mile 114 Richardson Hwy, Pump Station 11, Glennallen, AK 99588 | Lat: 62.087000; Long: -145.480000 | 1 tank | 5000 gal diesel tank |  | Advance approval required to transport soil or groundwater off-site. | 4/21/1998: Site Ranked Using the AHRM | Cleanup Complete
Residence-629 Tazlina Terrace | 629 Tazlina Terrace, Copperville Alaska, Glennallen, AK 99588 | Lat: 62.064844; Long: -145.410740 | 2 tanks | heating oil AST and UST |  | Movement or use of contaminated material (including on site) in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70). Advance approval required to transport soil or groundwater off site. | 5/24/2017: Cleanup Complete Determination issued | Cleanup Complete
Tazlina Copper Valley School | Former Copper Valley School, in the village of Tazlina south of Glennalen, Glennallen, AK 99588 | Lat: 62.047510; Long: -145.403060 | 60 acres | asbestos, unknown powder and grandular substances, releases from heating oil tanks, various uncontrolled dumps, lead acid batteries, paint |  | Movement or use of contaminated material (including on site) in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70). Advance approval required to transport soil or groundwater off site. | 2/4/2015: Cleanup Complete Determination Issued | Cleanup Complete
Tazlina River Dumpsite | N Bank of Tazlina River; -0.2 mile SE of Tazlina Former Copper Valley School, Tazlina, -6 mile SE of Glennallen, Glennallen, AK 99588 | Lat: 62.044612; Long: -145.401485 | 0.15 acres | dumpsite-residential refuse, construction debris, batteries, piping, drums, other metals, arsenic | John Carnahan | Notice of environmental contamination. Advance approval required to transport soil or groundwater off-site. Period reivew: report to DEC every 5 years. | 12/29/2022: Institutional Control Compliance Review: IC compliance review conducted. DEC received an IC review letter from the Archdiocese of Anchorage-Juneau on this date which documents that there have been no changes in land use. It also documents that the former dumpsite has not been disturbed and that the subsurface lead contamination remains buried. There may be a future change in land ownership as the Archdiocese and the Native Village of Tazlina (NVT) are in negotiations. | Cleanup Complete-Institutional Controls
ADOTPF-Tazlina Maintenance Station | Mi 110 Richardson Hwy, Glennallen, AK 99588 | Lat: 62.044059; Long: -145.424946 | Approx 2,000 cy | 8000 gal diesel UST, 8000 gal gas UST | IC Unit | CS Database Notation and letter to landowner/RP. When contaminated soil is accessible, remediation should occur. Advance approval required to transport soil or groundwater off-site. Movement or use of contaminated material in a manner that results in violation of the water quality standards is prohibited. Period review: 5 years. | 7/20/2022: Institutional Control Compliance Review: IC compliance review conducted after a site visit was performed by the IGAP coordinator for the Copper River Native Association. A site visit report and photos were provided to DEC and there were not any concerns found in regarding to the institutional controls. | Cleanup Complete-Institutional Controls
ADOT&PF Tazlina Maintenance Station Class V Injection Well | Mile 110 Richardson Hwy, Glennallen, AK 99588 | Lat: 62.044084; Long: -145.425712 |  | polycyclic aromatic hydrocarbon analytes, VOCs | Michael Hooper |  | 1/17/2024: Meeting or Teleconference Held: Annual Meeting Held with DOT to discuss plans for coming year at all NR UIC sites. | Active
Old BIA Copper Center School | Old Richardson Hwy, Approx 0.6 miles SE of Subdivision Road, Copper Center, AK 99573 | Lat: 61.972317; Long: -145.319573 |  | asbestos, petroleum | Gretchen Caudill |  | 2/28/2024: Site Characterization Report Approved: Approved Targeted Brownfields Assessment conducted by EPA. | Active
Copper Center Mountain View Gas & Liquor | Mile 100.8 Old Richardson Hwy, Copper Center, AK 99573 | Lat: 61.953975; Long: -145.305900 | 2 USTs | gas, benzene, toluene, ethylbenzene, diesel | Joshua Barsis |  | 5/23/2022: Workplan Requested: A workplan for disposal or treatment of the 80 cubic yards of waste and for further delineation was requested. | Active
AT&T Alascom TAPS Repeater Stuck | 25 miles S, SE of Glennallen, On hill overlooking Copper River Valley, Glennallen, AK 99588 | Lat: 61.790819; Long: -145.256078 | AST | petroleum | IC Unit | Advance approval required to transport soil or groundwater off-site. | 12/14/2011: Institutional Control record removed | Cleanup Complete
Vehicle Rollover MP 83.5 Richardson Highway | MP 83.5 Richardson Hwy, 17.5 miles South of Copper Center, Copper Center, Ak 99573 | Lat: 61.720842; Long: -145.163182 | 250 gal | 14,144 gal diesel, antifreeze, power steering fluid |  | Movement or use of contaminated material (including on site) in a manner that results in a violation of the water quality standards is prohibited (18 AAC 70). Advance approval required to transport soil or groundwater off site. | 3/27/2015: Cleanup Complete Determination Issued | Cleanup Complete
Kenny Lake Mercantile | Mile 7.5 Edgerton Hwy, Copper Center, AK 99573 | Lat: 61.736303; Long: -144.945505 | UST |  |  | Advance approval required to transport soil or groundwater off-site. | 1/20/2006: Update or other action: saw letter of no further action | Cleanup Complete
ADOTPF-Chitina Maintenance Station | Mi 33 Edgerton Hwy, Chitina, AK 99566 | Lat: 61.582000; Long: -144.435300 | Approx 180 cy | 2500 gal diesel tank, 2500 gas tank | IC Unit | Advance approval required to transport soil or groundwater off-site. | 9/26/2012: Institutional Control Record Removed | Cleanup Complete
Trading Post Café / Chitina Saloon | MP 33.3, Edgerton Hwy, Chitina, AK 99566 | Lat: 61.516702; Long: -144.437226 |  | diesel | Randy Guintu |  | 12/29/2023: Update or Other Action: In 1984 and 1985 petroleum was detected in the former Trading Post/Chitina Café’s drinking water well and two adjacent properties well. All wells were sampled for Oil & Grease using method 431.1 and indicated the potential presence of petroleum hydrocarbons and the site was added as an “active” contaminated site. In 1986, samples were collected from two of the wells located adjacent to the property and were analyzed for VOCs. VOCs were not detected. A release of a hazardous substance was never identified on this property or adjacent properties. In 2022, groundwater samples were collected from the drinking water well on the property and analyzed for GRO, DRO, VOCs, and PAHs. All analytes were not detected. Based on the environmental records for the site and the 2022 sampling event, DEC has decided that this site will be changed from “active” status to “non-qualifying” status. | Non-Qualifying
Strelna Roadhouse | Mile 15 McCarthy Road, Chitina, AK 99566 | Lat: 61.515354; Long: -144.439083 |  | petroleum hydrocarbons | IC Unit | Notice of environmental contamination. Advance approval required to transport soil or groundwater off-site. | 8/2/2023: Institutional Control Update: Received a Brownfield site visit report from Copper River Native Association which is included in their Brownfield inventory. There was difficulty in finding the site location but with the help of historic photos they were able to located it. Also provided as part of the report is a slight correction on lat/long coordinates which I have updated in this site record. There were no obvious signs of contamination on the property and the vegetation looked healthy. | Cleanup Complete-Institutional Controls
Chitina Power Plant | Upper Village Road Jct, with Lower Village Road, Chitina, AK 99566 | Lat: 61.510221; Long: -144.451257 | Approx 200 cy | 1500 gal diesel | Randy Guintu |  | 11/14/2019: Update or other action: emailed overdue report letter | Active
ADOT&PF Nelchina Maintenance Station Class V Injection Well | Mile 142.5 Glenn Highway, Glennallen, AK 99588 | Lat: 61.982835; Long: -146.841531 |  | one injection well | Michael Hooper |  | 1/17/2024: Meeting or Teleconference Held: Annual Meeting Held with DOT to discuss plans for coming year at all NR UIC sites. | Active
Eureka Lodge | MP 128 Glenn Highway; -30 miles W of Glennallen, Glennallen, AK 99588 | Lat: 61.938190; Long: -147.172120 | 20 gals | premium unleaded gas, diesel range organics, benzene, ethylbenzene, xylenes, heating oil | Grant Lidren |  | 10/15/2021: Update or Other Action: DEC sent letters to Crowley Fuels and to the Eureka Lodge owners requesting additional characterization to address data gaps, particularly to the south and west of the spill, to evaluated vapor intrusion in the nearby building, and to address questions about prior spills. | Active
ADOTPF-Paxson Maintenance Station | Mi 185.5 Richardson Hwy, Glennallen, AK 99588 | Lat: 63.033920; Long: -145.495527 | Approx 50 cy | diesel, gasoline, used oil | IC Unit | Excavation/Soil Movement Restrictions. Periodic Review: check with RP every three years. Advance approval required to transport soil or groundwater off site. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. Groundwater Use Restrictions: ADEC must be notified prior to installation of groundwater wells. | 2/25/2021: Institutional Control Compliance Review: IC compliance review conducted. A letter to the landowner was not issued. Set the reminder system to do a full compliance review in one year's time. | Cleanup Complete-Institutional Controls
FAA Gulkana | Mile 120 Richardson Hwy, Glennallen, AK 99588 | Lat: 62.159442; Long: -146.455413 |  | gasoline |  | Advance approval required to transport soil or groundwater off site. | 11/21/2012: Cleanup complete determination issued | Cleanup Complete
Former Lake Louise Convenience Store | Mile 160 Glenn Highway, Glennallen, AK 99588 | Lat: 62.087333; Long: -146.352310 |  | gas USTs, benzene |  | Advance approval required to transport soil or groundwater off site. | 6/10/2009: Leaking Underground Storage Tank Cleanup Initiated-petroleum | Cleanup Complete
Send International Maintenance Shop | Mile 187 Glenn Highway; Corner of College Rd and Drum Dr, Glennallen, AK 99588 | Lat: 61.111000; Long: -145.540000 |  | USTs 1 & 2, petroleum |  | Advance approval required to transport soil or groundwater off site. | 4/29/2009: Leaking Underground Storage Tank Cleanup Initiated-Petroleum | Cleanup Complete
ADOTPF-Nelchina Maintenance Station | Mile 142.5 Glenn Highway, Glennallen, AK 99588 | Lat: 62.102525; Long: -147.152960 |  | waste oil |  | Advance approval required to transport soil or groundwater off site. | 7/21/2008: Update or other action: file number given | Cleanup Complete
ADOTPF-Nelchina Maintenance Station | Mile 142.5 Glenn Highway, Glennallen, AK 99588 | Lat: 61.982300; Long: -146.840100 | Approx 60 cy | gasoline, diesel, used oil |  | Advance approval required to transport soil or groundwater off site. | 6/23/2004: Site Closure Approved | Cleanup Complete
Lake Louise Army Training Camp | 19.3 Mile Lake Louise Rd, Off Mile 159.8 Glenn Hwy, Glennallen, AK 99588 | Lat: 62.283889; Long: -146.525833 |  | mess hall remains and foundation, quonset hut remains, three latrines, the Marston landing mat/railroad tie breakwater and dock, barrck pads, property line fencing and posts and other visible debris |  |  | 2/6/2013: Final Cleanup Report Reviewed | Cleanup Complete
Alyeska PS 11 Block Valve 20 BL2 | Mile 114 Richardson Hwy, Pump Station 11, Glennallen, AK 99588 | Lat: 62.087000; Long: -145.480000 | 5 gals | diesel |  | Advance approval required to transport soil or groundwater off site. | 2/4/2004: Site Closure Approved | Cleanup Complete
AT&T Alascom TAPS Repeater Kimball Pass | 45 miles S, SE of Glennallen, Glennallen, AK 99588 | Lat: 61.512222; Long: -145.026667 |  | petroleum | IC Unit | Advance approval required to transport soil or groundwater off site. When contaminated soil is accessible, remediation should occur. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. | 8/15/2019: Institutional Control Compliance Review | Cleanup Complete-Institutional Controls
AT&T Alascom TAPS Repeater Round Top | 60 Miles N of Glennallen, Glennallen, AK 99588 | Lat: 62.803825; Long: -145.317842 |  | petroleum | IC Unit | Advance approval required to transport soil or groundwater off site. When contaminated soil is accessible, remediation should occur. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. | 8/1/2019: Instituional Control Compliance Review | Cleanup Complete-Institutional Controls
Tazlina River Trading Post | Mile 111.2 Richardson Hwy in Tazlina, Glennallen, AK 99588 | Lat: 62.063873; Long: -146.454712 | 1,000 cy | extensive hydrocarbon, benzene |  | Advance approval required to transport soil or groundwater off site. | 11/3/2004: Update or other action: file number issued | Cleanup Complete
Lake Louise Air Force Rec Camp | Former AF Rec Camp, End of Lake Louise Access, Glennallen, AK 99588 | Lat: 62.301163; Long: -146.590590 | 25 acres | diesel, building debris, concrete slabs and perimeter foundations | Kevin Fraley |  | 11/27/2023: Document, Report, or Work plan Review-other: Draft SRI report for the Tank Trailers Area received. 12/18/2023 Comments sent. 1/16/2024 Approval for final report sent. SRI was conducted to further delineate soil contamination at the TTA. Forty soil borings were advanced, and samples collected and analyzed for DRO and PAHs. Further removal action was recommended to remove remaining pockets of contamination. The supplemental SRA will take place in 2024. | Active
CVEA Glennallen Ethylene Glycol | Mile 187 Glenn Highway, Glennallen, AK 99588 | Lat: 62.109282; Long: -145.538696 | Approx 3 cy | ethylene glycol |  | Advance approval required to transport soil or groundwater off site. | 8/27/2001: Update or other action: notification letter | Cleanup Complete
Sourdough Roadhouse | MP 147.5 Richardson Hwy, Gakona, AK 99586 | Lat: 62.529080; Long: -145.517000 |  | benzene |  | Advance approval required to transport soil or groundwater off site. | 5/11/2006: Site Closure Approved | Cleanup Complete
Alyeska PLMP 734 Pipe Leak | Mile 65 Richardson Hwy, Pipeline Mile 734, Copper Center, AK 99573 | Lat: 61.487228; Long: -145.156862 | Approx 100 cy | crude oil | IC Unit | Advance approval required to transport soil or groundwater off site. Required every five years. When contaminated soil is accessible, remediation should occur. Instalation of groundwater wells will require approval from ADEC. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. | 3/30/2022: Institutional Control Compliance Review: Received Alyeska's IC verification letter on this date. There have been no land use changes or soil/groundwater moved from the site, etc. The next compliance review will be due in five years time. | Cleanup Complete-Institutional Controls
Alyeska PS 12 Mainline Turbine Sump | Mile 64.7 Richardson Hwy, Pipeline Mile 735 Copper Center, AK 99573 | Lat: 61.476054; Long: -145.145558 | 30 gals | MLT sump, petroleum, turbine fuel | IC Unit | Advance approval required to transport soil or groundwater off site. When contaminated soil is accessible, remediation should occur. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. Alyeska shall report to DEC every five years to document land use. | 3/12/2020: Institutional Control Compliance Review: The responsible party informed ADEC that there have been no changes in land use or ownership at this site since the 2010 Record of Decision. Reminder system re-set to follow up in 2025. IC compliance review conducted. Closure/IC Details updated. Reminder system already set for follow-up in 2020. | Cleanup Complete-Institutional Controls
Alyeska PS 12 Fuel Island Area | Mile 64.7 Richardson Hwy, Pipeline Mile 735 Copper Center, AK 99573 | Lat: 61.475900; Long: -145.145300 |  | turbine fuel, diesel |  | Advance approval required to transport soil or groundwater off site. | 5/2/2013: Cleanup Complete Determination Issued | Cleanup Complete
Powerhouse Fuel Tank Farm | Kennicott, McCarthy, Chitina, AK 99566 | Lat: 61.486380; Long: -142.886390 | Approx 79,000 sq ft | leaking tank and other unknown sources |  | Advance approval required to transport soil or groundwater off site. | 3/10/1995: Update or other action: remedial action report review | Cleanup Complete
NPS Kennicott Mine | Kennicott, McCarthy, Chitina, AK 99566 | Lat: 61.484650; Long: -142.887750 | Approx 300 sq ft | transformer oil, lube oil/grease | Gretchen Caudill |  | 2/24/2023: Meeting or Teleconference Held: ADEC met with NPS and representatives from Ahtna to discuss multiple site histories and potential paths forward for remediation and eventual closure with or without Ics. | Active
NPS Kennicott Mine Monroe Tank 4(1) | Kennicott, McCarthy, Chitina, AK 99566 | Lat: 61.487903; Long: -142.890195 |  | petroleum | Gretchen Caudill |  | 8/17/2022: Meeting or Teleconference Held: ADEC met with NPS and representatives from Ahtna to discuss multiple site histories and potential paths forward for remediation and eventual closure with or without Ics. | Active
NPS Kennicott Mine Lead Paint | Kennicott, McCarthy, Chitina, AK 99566 | Lat: 61.484680; Long: -142.887880 |  | lead | Gretchen Caudill |  | 8/17/2022: Meeting or Teleconference Held: ADEC met with NPS and representatives from Ahtna to discuss multiple site histories and potential paths forward for remediation and eventual closure with or without Ics. | Active
ADOTPF-O'Brien Creek, UL T-235-2A | O'Brien Creek; Mile 113 Taylor HWY, Chitina, AK 99566 | Lat: 64.316828; Long: -141.418246 | Approx 160 cy | diesel, unleaded gas, used oil, arsenic | IC Unit | Groundwater use restrictions. Advance approval required to transport soil or groundwater off site. When contaminated soil is accessible, remediation should occur. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. Review of site conditions every three years. | 6/20/2018: Institutional Control Compliance Review | Cleanup Complete-Institutional Controls
FAA Summit NDB/RCO | Mile 201 Parks Highway, -9 mile S of Cantwel, Cantwell, AK 99729 | Lat: 63.331035; Long: -149.129614 | Approx 800 cy | petroleum hydrocarbon, diesel, gas | John O'Brien |  | 3/19/2021: Document, Report, or Work plan Review-other: Received Draft Summit FAA Station Long Term Monitoring Report dated February 2021. DEC comments sent March 4, 2021. RTC received March 12, 2021.Approval sent 5/27/21. | Active
FAA Summit Former Tank Farm | Mile 201 Parks Highway, -9 mile S of Cantwel, Cantwell, AK 99729 | Lat: 63.331035; Long: -149.129614 |  | petroleum | John O'Brien |  | 3/19/2021: Document, Report, or Work plan Review-other: Received Draft Summit FAA Station Long Term Monitoring Report dated February 2021. DEC comments sent March 4, 2021. RTC received March 12, 2021.Approval sent 5/27/21. | Active
FAA Summit Flight Service Station | Mile 201 Parks Highway, -9 mile S of Cantwel, Cantwell, AK 99729 | Lat: 63.331035; Long: -149.129614 | Approx 7,000 gals | diesel, asbestos, PCBs, debris | John O'Brien |  | 3/19/2021: Document, Report, or Work plan Review-other: Received Draft Summit FAA Station Long Term Monitoring Report dated February 2021. DEC comments sent March 4, 2021. RTC received March 12, 2021.Approval sent 5/27/21. | Active
FAA Summit Radio Range | Mile 201 Parks Highway, -9 mile S of Cantwel, Cantwell, AK 99729 | Lat; 63.313569; Long: -149.189787 | Approx 70 cy | petroleum hydrocarbon, chlorinated herbicide 2, 4-D, 5-T, diesel |  | Advance approval required to transport soil or groundwater off site. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. | 6/19/2019: Update or other action: site location updated | Cleanup Complete
Valdez Creek Mine-Waste Motor Oil | Denali Highway, Cantwell, AK 99729 | Lat: 63.103947; Long: -147.539772 | Approx 50,000 gals | waste motor oil |  | Advance approval required to transport soil or groundwater off site. | 5/21/1990: Site closure approved | Cleanup Complete
FAA Summit Air Navigation Site-Sitewide | Mile 201 Parks Highway, Quarters & Service Area, Cantwell, AK 99729 | Lat: 63.331035; Long: -149.129614 | Approx 2 acres | diesel, diesel, gas | John O'Brien |  | 3/19/2021: Document, Report, or Work plan Review-other: Received Draft Summit FAA Station Long Term Monitoring Report dated February 2021. DEC comments sent March 4, 2021. RTC received March 12, 2021.Approval sent 5/27/21. | Active
Valdez Creek Mine-Collective Areas | Denali Highway, Cantwell, AK 99729 | Lat: 63.103947; Long: -147.539772 | Approx 5,000 gals | diesel, waste oil, antifreeze |  | Advance approval required to transport soil or groundwater off site. | 2/24/2004: Update or other action: file number assigned. | Cleanup Complete
Valdez Creek Mine-Dam Blow-Out | Denali Highway, Cantwell, AK 99729 | Lat: 63.106189; Long: 147.526800 | Approx 60 million gals | water reservoir carrying mining tailings-metals, turbidity, settable solids |  | Advance approval required to transport soil or groundwater off site. | 5/25/1995: Site Number Identifier Changed | Cleanup Complete
Drashner Homestead | Mile 131 Denali Highway, Cantwell, AK 99729 | Lat: 63.371748; Long: -148.829816 |  | diesel | Shawn Tisdell |  | 1/3/2022: Update or Other Action: Correspondence with the RP indicates site conditions and use have not significantly changed since the 2019 site visit. Current and future site use is not expected to increase risk of exposure to releases that occurred at the site. | Active
AT&T Alascom Honolulu Repeater | Mile 180 Parks Highway, Cantwell, AK 99729 | Lat: 63.094722; Long: -149.505278 |  | diesel |  | Advance approval required to transport soil or groundwater off site. | 11/26/2001: Site Closure Approved | Cleanup Complete
AT&T Alascom Cantwell Repeater | 1.5 Mile W of Airport, Cantwell, AK 99729 | Lat: 63.401111; Long: -148.937778 |  | diesel |  | Advance approval required to transport soil or groundwater off site. | 1/4/2022: Update or Other Action: Updated lat/long based on current geographic information. | Cleanup Complete
ARRC Summit Siding | ARRC Mile Post 312.5, Near Summit Lake, Cantwell, AK 99729 | Lat: 63.327396; Long: -149.126229 | Approx 20 cy | weathered gasoline and diesel | Grant Lidren |  | 1/26/2011: Update or other action: no work was ever performed. | Active
USPS Cantwell Post Office | Mile 210 George Parks Hwy, 0.1 Mi N of Denali Hwy, Cantwell, AK 99729 | Lat: 63.391885; Long: -148.901105 | Approx 150 cy | diesel, heating oil | Jamie McKellar |  | 6/16/2021: Document, Report, or Work plan Review-other: Draft WP for one 5 point composite sample collection this month or next, received. 6/23/2021: comments sent. Final WP received 8/2/2021. Approval sent 8/9/2021. | Active
ARRC Cantwell Section House | Intersection Denali Hwy, and railroad mainline, Cantwell, AK 99729 | Lat: 63.391147; Long: -148.952697 |  | potential contaminated concentrations | IC Unit | Advance approval required to transport soil or groundwater off site. | 7/9/2012: Institutional Control Record Review | Cleanup Complete
ADOTPF-Cantwell Maintenance Station | Mile 135 Denalie Highway, Cantwell, AK 99729 | Lat: 63.388998; Long: -148.885004 | Approx 75 cy | used oil, diesel, gas, benzene | IC Unit | Advance approval required to transport soil or groundwater off site. | 12/14/2011: Institutional Control record removed | Cleanup Complete
ARRC-Broad Pass Railroad Station | Mile 304.5 Alaska Railrd; MP 193 Parks Highway, Cantwell, AK 99729 | Lat: 63.235438; Long: -149.268617 | 1/2 acre | diesel | IC Unit | Advance approval required to transport soil or groundwater off site. Excavation/Soil movement restrictions. | 2/24/2023: Institutional Control Compliance Review: IC compliance review conducted on this date and a reminder letter was issued. The next compliance review will be in 5yrs. | Cleanup Complete-Institutional Controls
ADOTPF-Chulitna Wayside | MP 185.5 Parks Hwy, Cantwell, AK 99729 | Lat: 63.151518; Long: -149.410605 | one UST | diesel, gas, benzene |  | Advance approval required to transport soil or groundwater off site. | 5/16/2005: Site Closure Approved | Cleanup Complete
Tesoro-Tsesyu-Parks Hwy. | Mile 210 Parks Hwy; Denali Hwy, Cantwell, AK 99729 | Lat: 63.389897; Long: -148.903642 | two USTs | unleaded gas, diesel, benzene, toluene, ethyl benzene, xylene |  | Advance approval required to transport soil or groundwater off site. | 2/11/1997: Site Closure Approved | Cleanup Complete
ARRC-Cantwell Station | ARR mile 319.5 Cantwell, AK 99729 | Lat: 63.391200; Long: -148.953090 | UST | petroleum |  | Advance approval required to transport soil or groundwater off site. | 6/11/1996: Site Closure Approved | Cleanup Complete
Reindeer Mountain Lodge | Mile 209 Geo Parks Hwy Lot 25 B- C & D Cantwell Small Tracts, Cantwell, AK 99729 | Lat: 63.387049; Long: -148.904912 | Approx 45 cy | reg and unleaded gasoline | IC Unit | Advance approval required to transport soil or groundwater off site. | 12/5/2014: Update or Other Action: drinking water well sampling showed non-detect concentrations | Cleanup Complete
ADOTPF-East Fork Maintenance Station | MP 185 Parks Hwy Cantwell, AK 99729 | Lat: 63.144200; Long: -149.424200 | Approx 700 cy | diesel, gasoline, used oil, benzene | IC Unit | Advance approval required to transport soil or groundwater off site. Groundwater use restrictions. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. Periodic review-every three years. | 6/2/2021: Update or Other Action: Responded to Temporary Water Use Authorization application A2021-79 received from DNR, source intake located adjacent to the site in the Chulitna River. IC unit had no comments or concerns on the use of water near the site. | Cleanup Complete-Institutional Controls
ARRC Broad Pass Railroad Station | MP 193 Parks Highway; ARRC MP 304.5; -15 m SW of Cantwell, Cantwell, AK 99729 | Lat: 63.235530; Long: -149.268670 | one UST | diesel heating oil | IC Unit | Advance approval required to transport soil or groundwater off site. | 2/24/2023: Institutional Control Compliance Review: IC compliance review conducted on this date and a reminder letter was issued. The next compliance review will be in 5yrs. | Cleanup Complete-Institutional Controls
Nenana Heating Services Truck Rollover-MP 134.5 Denali Highway | Milepost 134.5 Denali Highway, Cantwell, AK 99729 | Lat: 63.392324; Long: -148.913708 | 260 gals | ultra low sulfur #1 diesel fuel |  | Advance approval required to transport soil or groundwater off site. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. | 5/5/2017: Cleanup Complete Determination Issued | Cleanup Complete
ADOT&PF Cantwell Maintenance Station Class V Injection Well | Milepost 135 Denali Highway Cantwell, AK 99729 | Lat: 63.389141; Long: -148.884484 | underground injection well | metals, VOCs, SVOCs | Michael Hooper |  | 1/31/2023: Institutional Control Record Removed: Institutional Controls have been removed. | Cleanup Complete
Lynden Transport Vehicle Accident-MP 169 Parks Highway | MP 169 Parks Highway; ARRC MP 279.6 Crossing; -41 m S of Cantwell, Cantwell, AK 99729 | Lat: 62.952536; Long: -149.657994 | Approx 200 gals | diesel, petroleum |  | Advance approval required to transport soil or groundwater off site. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. | 5/20/2016: Institutional Control Record Removed | Cleanup Complete
FAA Summit Former Housing South | Mile 201 Parks Highway Cantwell, AK 99729 | Lat: 63.327011; Long: -149.132119 |  | petroleum, diesel, polycyclic aromatic hydrocarbons | John O'Brien |  | 3/19/2021: Document, Report, or Work plan Review-other: Received Draft Summit FAA Station Long Term Monitoring Report dated February 2021. DEC comments sent March 4, 2021. RTC received March 12, 2021.Approval sent 5/27/21. | Active
FAA Summit Former Housing North | Mile 201 Parks Highway Cantwell, AK 99729 | Lat: 63.327500; Long: -149.134192 |  | petroleum, gas, diesel, polycyclic aromatic hydrocarbons |  | Advance approval required to transport soil or groundwater off site. Movement or use of contaminated material in a manner that results in a violation of the water quality standards is prohibited. | 7/3/2018: Cleanup Complete Determination Issued | Cleanup Complete
FAA Summit Former Gasoline Pumphouse and AST | Mile 201 Parks Highway Cantwell, AK 99729 | Lat: 63.328442; Long: -149.134136 | AST | gas, diesel, benzene, ethylbenzene, polycyclic aromatic hydrocarbons | John O'Brien |  | 3/19/2021: Document, Report, or Work plan Review-other: Received Draft Summit FAA Station Long Term Monitoring Report dated February 2021. DEC comments sent March 4, 2021. RTC received March 12, 2021.Approval sent 5/27/21. | Active
Igloo City USTs | Mile 188.5 Parks Highway; -19.5 m SW of Cantwell, Cantwell, AK 99729 | Lat: 63.188040; Long: -149.359925 | Approx 100 cy | petroleum, gas, diesel | Bill O'Connell |  | 10/27/2021: Workplan Requested: Following a file review, staff provided the RP with a summary of data gaps in site characterization information and requested a work plan. | Active